## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shivangi | 2025-11-25 | Missing values in Salary column preventing calculations. | Sprint 1 | Shivangi | Logical | Used pd.to_numeric with error handling. | 2025-11-20 | Closed
2 | Shivangi | 2025-12-09 | Overlapping subplots in multi-visualization charts. | Sprint 2 | Shiavngi | User Interface | Applied plt.tight_layout() for better spacing. | 2025-12-05 | Closed
3 | Shivangi | 2025-12-23 | Mismatch in Image-Annotation pairs in Google Drive. | Sprint 3 | Shivangi | Standards | Scripted a validation check using os and glob. | 2025-12-19 | Closed
4 | Shivangi | 2026-01-07 | Redundant counting of stationary vehicles in video feed. | Sprint 4 | Shivangi | Logical | Implemented object tracking IDs to ensure unique counts. | 2026-01-05 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others